## Preliminaries
Page | Item | Description | Uom | Quantity | Rate | Amount | Total | x | Formatted Qty | x | Abstract RecID | x | Lcode | x | x | x | x | x | x | x | x | x | x | x | x | Package | Section | Bill | Trade | Type | ABUm | PayRef
|  | SECTION NO. 0 : Single Section | [23 empty] | 1 | 0 | 1 | -2 | H
NOTE: the column headings a - z must be present for the importer.
These contain an X which is set forecolor = white
|  | BILL NO.1 : PRELIMINARIES | [23 empty] | 1 | 0 | 1 | -2 | H
1 |  | PRELIMINARIES | [8 empty] | 1 |  | 78460 | [12 empty] | 1 | 0 | 1 | -2 | H | 0
1 |  | Disclaimer | [8 empty] | 2 |  | 78470 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | While the ASAQS aims to ensure that its publications represent best practice, the ASAQS does not accept or assume any liability or responsibility for any events or consequences which derive from the use of the Preliminaries Master Bill. Such Master Bill is not exhaustive and is therefore only intended to provide general guidance to those who wish to make use of it. This publication is provided 'as is' without warranty of any kind, either expressed or implied including but without limitation to warranties of merchantability, fitness for a particular purpose and non-infringement | [8 empty] | 2 |  | 78470 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | User note: | [8 empty] | 2 |  | 78470 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | Delete the above Disclaimer when preparing this Bill No 1 for tender or contract purposes. Hereinafter edit all text, etc but even more specifically text within ?...? to ensure that such text applies to the specific project or contract | [8 empty] | 2 |  | 78470 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
1 |  | BUILDING AGREEMENT AND PRELIMINARIES | [8 empty] | 3 |  | 78510 | [12 empty] | 1 | 0 | 1 | -2 | H | 0
1 |  | The JBCC Principal Building Agreement (March 2014 Edition 6.1) prepared by the Joint Building Contracts Committee shall be the applicable building agreement, amended as hereinafter described | [8 empty] | 4 |  | 78520 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
1 |  | The JBCC Principal Building Agreement contract data form an integral part of this agreement | [8 empty] | 5 |  | 78530 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
1 |  | The Preliminaries Revision 1 (February 2016) published by the Association of South African Quantity Surveyors for use with the JBCC Principal Building Agreement shall be deemed to be incorporated in these bills of quantities, amended as hereinafter described | [8 empty] | 6 |  | 78540 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
1 |  | The contractor is deemed to have referred to the abovementioned documents for the full intent and meaning of each clause | [8 empty] | 7 |  | 78550 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
1 |  | The clauses in the abovementioned documents are hereinafter referred to by clause number and heading only. | [8 empty] | 8 |  | 78560 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
1 |  | Where any item is not relevant to this agreement such item is marked N/A (signifying not applicable) | [8 empty] | 9 |  | 78570 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
1 |  | USER NOTE | [8 empty] | 10 |  | 163253 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | A provision/clause in Edition 6.1 of the JBCC Principal Building Agreement may have unintended consequences. The following is relevant: | [8 empty] | 10 |  | 163253 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | Within the contract data document there is space to insert changes made to the JBCC documentation. Quantity surveyors have generally up to now merely inserted in this space "Refer to Bill No. 1". | [8 empty] | 10 |  | 163253 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | Below the abovementioned space the following note has been inserted: | [8 empty] | 10 |  | 163253 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | Note : The amendments contained herein or in the single referenced Annexure constitute the only amendments to the standard JBCC Agreement that will apply. No other amendments shall be of any force or effect' | [8 empty] | 10 |  | 163253 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | Should quantity surveyors wish to adhere to the system of inserting amendments, modifications, corrections or supplements to the JBCC documentation under the listed clause headings in Bill No. 1 (Preliminaries) then it is suggested that the following clause be inserted in the space provided in the contract data where changes made to the JBCC documentation are to be recorded: | [8 empty] | 10 |  | 163253 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | It is specifically agreed that the note below calling for amendments to the standard JBCC Agreement to be listed in the space provided in the contract data or recorded in 'the single referenced Annexure' shall not apply . Where standard clauses or alternatives are not entirely applicable to this agreement such amendments, modifications, corrections or supplements as will apply are given under each relevant clause heading in Bill No 1 (Preliminaries) and such amendments, modifications, corrections or supplements shall take precedence notwithstanding the note below and notwithstanding the provisions of clause 5.6 of the JBCC Principal Building Agreement' | [8 empty] | 10 |  | 163253 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | Not doing as suggested above when adhering to the system generally used by quantity surveyors up to now may result in any amendments within Bill No. 1 (Preliminaries) being considered null and void, which could then lead to major claims | [8 empty] | 10 |  | 163253 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
2 |  | The following paragraph should in addition be inserted | [8 empty] | 11 |  | 163263 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | ? Where standard clauses or alternatives are not entirely applicable to this agreement such amendments, modifications, corrections or supplements as will apply are given under each relevant clause heading and such amendments, modifications, corrections or supplements shall take precedence notwithstanding anything to the contrary contained in the abovementioned documents ? | [8 empty] | 11 |  | 163263 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
2 |  | PREAMBLES FOR TRADES | [8 empty] | 12 |  | 78580 | [12 empty] | 1 | 0 | 1 | -2 | H | 0
2 |  | USER NOTE | [8 empty] | 13 |  | 163023 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | The Model Preambles for Trades 2008 published by the Association of South African Quantity Surveyors is designed to support and extend the abbreviated descriptions utilised in these bills of quantities by inter alia referring to SANS construction standards. Where such model preambles are not applicablenone (eg where BS or Euro construction standards are applicable or the design consultants provide other preambles/specifications for insertion), users are to ensure that the abbreviated descriptions when read in conjunction with the Standard System of Measuring Building Work (seventh edition) for works within South Africa or the Standard Method of Measuring Building Work for Africa 2015 (first edition) for works elsewhere in Africa, represent the full description by extending the abbreviated bills of quantities descriptions and/or by inserting appropriate preambles or specifications | [8 empty] | 13 |  | 163023 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | Note that the text of the Standard System of Measuring Building Work (seventh edition) and that of the Standard Method of Measuring Building Work for Africa 2015 (first edition) is the same | [8 empty] | 13 |  | 163023 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
3 |  | The Model Preambles for Trades 2008 as published by the Association of South African Quantity Surveyors shall be deemed to be incorporated in these bills of quantities and no claims arising from brevity of description of items fully described in the said Model Preambles will be entertained | [8 empty] | 14 |  | 78590 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
3 |  | Note that the text of the Standard System of Measuring Building Work (seventh edition) and that of the Standard Method of Measuring Building Work for Africa 2015 (first edition) is the same | [8 empty] | 15 |  | 163013 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
3 |  | Supplementary preambles and/or specifications are incorporated in these bills of quantities to satisfy the requirements of this project. Such supplementary preambles and/or specifications shall take precedence over the provisions of the Model Preambles | [8 empty] | 16 |  | 78600 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
3 |  | The contractor's prices for all items throughout these bills of quantities shall take account of and include for all of the obligations, requirements and specifications given in the Model Preambles and in any supplementary preambles and/or specifications | [8 empty] | 17 |  | 78610 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
3 |  | STRUCTURE OF THIS PRELIMINARIES BILL | [8 empty] | 18 |  | 163033 | [12 empty] | 1 | 0 | 1 | -2 | H | 0
3 |  | Section A : A recital of the headings of the individual clauses of the aforementioned JBCC Principal Building Agreement | [8 empty] | 19 |  | 163273 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
3 |  | Section B : A recital of the headings of the individual clauses of the aforementioned Preliminaries document | [8 empty] | 20 |  | 163283 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
3 |  | Section C : Any special clauses to meet the particular circumstances of the project | [8 empty] | 21 |  | 163293 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
3 |  | PRICING OF PRELIMINARIES | [8 empty] | 22 |  | 78620 | [12 empty] | 1 | 0 | 1 | -2 | H | 0
3 |  | Should the contractor select Option A in the contract data for the adjustment of preliminaries , the amounts entered against the relevant items in these preliminaries are to be divided into one or more of the three categories provided namely fixed (F), value related (V) and time related (T) | [8 empty] | 23 |  | 78630 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
3 |  | SECTION A: PRINCIPAL BUILDING AGREEMENT | [8 empty] | 24 |  | 78640 | [12 empty] | 1 | 0 | 1 | -2 | H | 0
3 |  | Interpretation (A1 - A7) | [8 empty] | 25 |  | 78650 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
3 | 1 | Clause 1.0 - Definitions and interpretation | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Definition of agreement | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The definition of agreement is replaced with the following definition : | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | AGREEMENT : The JBCC Principal Building Agreement, the completed JBCC PBA contract data, the contract drawings, the priced documents and any other documents reduced to writing and signed by the parties' | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Pricing of bills of quantities | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor is to allow opposite each item for all costs in connection therewith. All prices to include, unless otherwise stated, for all materials, fabrication, conveyance and delivery, unloading, storing, unpacking, hoisting, labour, setting, fitting and fixing in position, cutting and waste (except where to be measured in accordance with the standard system of measurement), patterns, models and templates, plant, temporary works, returning of packaging, duties, taxes (other than Value Added Tax), imposts, establishment charges, overheads, profit and all other obligations arising out of this agreement . Value Added Tax (VAT) is to be separately stated on the summary page of these bills of quantities | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Items left unpriced will be deemed to be covered in prices against other items throughout these bills of quantities and no claim for any extras arising out of the contractor's omission to price any item will be entertained | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Prices for all construction equipment, temporary works, services and other items shall include for the supply, maintenance, operating cost and subsequent removal and making good as necessary | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Abbreviated descriptions | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The items in these bills of quantities utilise abbreviated descriptions. It is the intention that the abbreviated descriptions be fully described when read with the applicable measuring system and the relevant preambles and/or specifications. However, should the full intent and meaning of any description not be clear, the contractor shall, before submission of his tender, call for a written directive from the principal agent , failing which it shall be assumed that the contractor has allowed in his pricing for materials and workmanship in terms of international best practice | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Legal status of contractor | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | If the contractor constitutes a joint venture, consortium or other unincorporated grouping of two or more persons then: | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1. These persons are deemed to be jointly and severally liable to the employer for the performance of this agreement | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2. These persons shall notify the employer of their leader who has authority to bind the contractor and each of these persons | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3. The contractor shall not alter its composition or legal status without the prior written consent of the employer | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Omit from definition of construction period the words : 'excluding annual holiday periods' Omit from definition of preliminaries the word : 'priced' | Item | 1 |  | 0 |  |  | 1 |  | 26 |  | 78660 | [12 empty] | 1 | 0 | 1 | -2 | I | I
4 | 2 | Clause 2.0 - Law, regulations and notices | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following where a health and safety specification is NOT yet available | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?Health and safety | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Without limiting the generality of the provisions of clause 2.0, the contractor's attention is drawn to the provisions of Construction Regulations issued in terms of the Occupational Health and Safety Act, 1993. It is specifically stated that the employer shall prepare a documented health and safety specification for the works and that the employer shall ensure that the contractor has made provision for the cost of health and safety measures during the execution of the works. The contractor shall price opposite this item for compliance with the act and the regulations and the reasonable provisions of the aforementioned health and safety specification [2.1] ? | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following where a health and safety specification IS available | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?Health and safety | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Without limiting the generality of the provisions of clause 2.0, the contractor's attention is drawn to the provisions of Construction Regulations issued in terms of the Occupational Health and Safety Act, 1993. It is specifically stated that the employer shall prepare a documented health and safety specification for the works (refer to Annexure ? for a copy of the relevant specification) and that the employer shall ensure that the contractor has made provision for the cost of health and safety measures during the execution of the works . The contractor shall price opposite this item for compliance with the act and the regulations and the provisions of the aforementioned health and safety specification [2.1] ? | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor shall: | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1. Comply with the health and safety specification for the works | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2. Prepare and agree with the health and safety consultant the health and safety plan for the works | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3. Co-operate with the health and safety consultant in all respects | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4. Manage the compliance of all subcontractors with the regulations and with the health and safety plan and specification | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5. Conform to the conditions contained in the employer's safety specification | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert ONE of the following for residential developments only | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? NHBRC levies | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The employer shall allow for and pay any levies required by the National Home Builders Registration Council (NHBRC). The contractor warrants that he is registered and will maintain registration with the NHBRC for the duration of this agreement [2.1] ? | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? NHBRC levies | [8 empty] | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The employer shall allow for and pay any levies required by the National Home Builders Registration Council (NHBRC). The contractor warrants that he is registered and will maintain registration with the NHBRC for the duration of this agreement [2.1] ? | Item | 1 |  | 0 |  |  | 1 |  | 27 |  | 78670 | [12 empty] | 1 | 0 | 1 | -2 | I | I
6 | 3 | Clause 3.0 - Offer and acceptance | Item | 1 |  | 0 |  |  | 1 |  | 28 |  | 78680 | [12 empty] | 1 | 0 | 1 | -2 | I | I
6 | 4 | Clause 4.0 - Assignment and cession | Item | 1 |  | 0 |  |  | 1 |  | 29 |  | 78690 | [12 empty] | 1 | 0 | 1 | -2 | I | I
6 | 5 | Clause 5.0 - Contract documents | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Value Added Tax | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Provision is made in the summary page of these bills of quantities for the inclusion of Value Added Tax (VAT) | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contract drawings are to be listed in the contract data. If insufficient space is available for such listing or for any other reason then reference should be made in the contract data as to where the contract drawings are listed. One of the following clauses may be used | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following where only a few contract drawings are applicable | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?Contract drawings | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contract drawings are as listed on the contents page of the bills of quantities [5.1] ? | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following where numerous contract drawings are applicable | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?Contract drawings | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Refer to Annexure ? for a list of the contract drawings [5.1] ? | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Priced document as specification | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 5.3 is deemed to be deleted | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The principal agent shall decide which portion of the priced document may be used as a specification of materials and goods or methods, if any | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following where applicable | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?Electronic issue of drawings | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | All drawings for this project will be issued electronically and the contractor shall be deemed to have received such drawings on the date that such drawings have been dispatched electronically [5.5] | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Precedence | [8 empty] | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 5.6 is deemed to be deleted. The provisions of the Bill No. 1 (Preliminaries) shall take precedence over any other documents which constitute this agreement [5.6] | Item | 1 |  | 0 |  |  | 1 |  | 30 |  | 78700 | [12 empty] | 1 | 0 | 1 | -2 | I | I
6 | 6 | Clause 6.0 - Employer's agents | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Delegated authority | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The authority of the principal agent to issue contract instructions and perform duties for specific aspects of the works is delegated to agents as follows [7.2]: ? | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User Note | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Add delegated authority as may be required for other relevant consultants not listed hereinafter | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? 1. Architect | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User Note | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following but remove where the consultant is not relevant to this agreement. Edit both the duties and the contract instructions of the consultant in keeping with the wishes of the principal agent | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Note that the contract instructions hereinafter are those listed in clause 17.0 of the JBCC PBA | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.1 Duties : The architect is responsible for the architectural design, functional design and quality inspection of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2 Contract instructions [17.0] : | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.1 Rectification of discrepancies, errors in descriptions or omissions in contract documents other than this agreement | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.3 The site [13.2.4] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.4 Compliance with the law , regulations and bylaws [2.1] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.5 Provision and testing of samples of materials and goods , of finishes and assemblies of elements of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.6 Opening up of work for inspection, removal or re-execution | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.7 Removal or re-execution of work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.8 Removal or substitution of any materials and goods | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.9 Protection of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.10 Making good physical loss and repairing damage to the works [8.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.11 Rectification of defects [21.2] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.12 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion and a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.13 Expenditure of budgetary allowances , prime cost amounts and provisional sums | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.14 Appointment of a subcontractor [14.0; 15.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.15 Termination of a nominated n/s subcontract agreement [27.2.8] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.16 Work by (a) direct contractor (s) [17.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.17 Access by other or previous contractors to remedy defective work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.18 Removal from the site of any person employed on the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.19 Removal from the site of any person not engaged on or connected with the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1.2.20 On termination, protection of the works , removal of construction equipment and surplus materials and goods [29.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? 2. Quantity surveyor | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following but remove where the consultant is not relevant to this agreement. Edit both the duties and the contract instructions of the consultant in keeping with the wishes of the principal agent | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Note that the contract instructions hereinafter are those listed in clause 17.0 of the JBCC PBA | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.1 Duties : The quantity surveyor is responsible for all measurements, valuations, financial assessments and all other quantity surveying and cost control functions of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2 Contract instructions [17.0] : | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.1 Rectification of discrepancies, errors in descriptions or omissions in contract documents other than this agreement | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.3 The site [13.2.4] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.4 Compliance with the law , regulations and bylaws [2.1] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.5 Provision and testing of samples of materials and goods , of finishes and assemblies of elements of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.6 Opening up of work for inspection, removal or re-execution | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.7 Removal or re-execution of work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.8 Removal or substitution of any materials and goods | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.9 Protection of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.10 Making good physical loss and repairing damage to the works [8.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.11 Rectification of defects [21.2] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.12 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion and a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.13 Expenditure of budgetary allowances , prime cost amounts and provisional sums | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.14 Appointment of a subcontractor [14.0; 15.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.15 Termination of a nominated n/s subcontract agreement [27.2.8] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.16 Work by (a) direct contractor (s) [17.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.17 Access by other or previous contractors to remedy defective work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.18 Removal from the site of any person employed on the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.19 Removal from the site of any person not engaged on or connected with the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2.2.20 On termination, protection of the works , removal of construction equipment and surplus materials and goods [29.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?3. Civil and structural engineer | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following but remove where the consultant is not relevant to this agreement. Edit both the duties and the contract instructions of the consultant in keeping with the wishes of the principal agent | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Note that the contract instructions hereinafter are those listed in clause 17.0 of the JBCC PBA | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.1 Duties : The civil and structural engineer is responsible for all measurements, valuations, financial assessments and all other quantity surveying and cost control functions of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2 Contract instructions [17.0] : | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.1 Rectification of discrepancies, errors in descriptions or omissions in contract documents other than this agreement | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.3 The site [13.2.4] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.4 Compliance with the law , regulations and bylaws [2.1] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.5 Provision and testing of samples of materials and goods , of finishes and assemblies of elements of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.6 Opening up of work for inspection, removal or re-execution | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.7 Removal or re-execution of work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.8 Removal or substitution of any materials and goods | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.9 Protection of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.10 Making good physical loss and repairing damage to the works [8.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.11 Rectification of defects [21.2] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.12 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion and a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.13 Expenditure of budgetary allowances , prime cost amounts and provisional sums | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.14 Appointment of a subcontractor [14.0; 15.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.15 Termination of a nominated n/s subcontract agreement [27.2.8] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.16 Work by (a) direct contractor (s) [17.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.17 Access by other or previous contractors to remedy defective work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.18 Removal from the site of any person employed on the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.19 Removal from the site of any person not engaged on or connected with the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3.2.20 On termination, protection of the works , removal of construction equipment and surplus materials and goods [29.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?4. Mechanical engineer | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following but remove where the consultant is not relevant to this agreement. Edit both the duties and the contract instructions of the consultant in keeping with the wishes of the principal agent | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Note that the contract instructions hereinafter are those listed in clause 17.0 of the JBCC PBA | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.1 Duties : The mechanical engineer is responsible for all measurements, valuations, financial assessments and all other quantity surveying and cost control functions of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2 Contract instructions [17.0] : | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.1 Rectification of discrepancies, errors in descriptions or omissions in contract documents other than this agreement | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.3 The site [13.2.4] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.4 Compliance with the law , regulations and bylaws [2.1] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.5 Provision and testing of samples of materials and goods , of finishes and assemblies of elements of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.6 Opening up of work for inspection, removal or re-execution | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.7 Removal or re-execution of work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.8 Removal or substitution of any materials and goods | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.9 Protection of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.10 Making good physical loss and repairing damage to the works [8.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.11 Rectification of defects [21.2] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.12 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion and a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.13 Expenditure of budgetary allowances , prime cost amounts and provisional sums | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.14 Appointment of a subcontractor [14.0; 15.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.15 Termination of a nominated n/s subcontract agreement [27.2.8] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.16 Work by (a) direct contractor (s) [17.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.17 Access by other or previous contractors to remedy defective work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.18 Removal from the site of any person employed on the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.19 Removal from the site of any person not engaged on or connected with the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4.2.20 On termination, protection of the works , removal of construction equipment and surplus materials and goods [29.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?5. Electrical engineer | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following but remove where the consultant is not relevant to this agreement. Edit both the duties and the contract instructions of the consultant in keeping with the wishes of the principal agent | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Note that the contract instructions hereinafter are those listed in clause 17.0 of the JBCC PBA | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.1 Duties : The electrical engineer is responsible for all measurements, valuations, financial assessments and all other quantity surveying and cost control functions of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2 Contract instructions [17.0] : | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.1 Rectification of discrepancies, errors in descriptions or omissions in contract documents other than this agreement | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.3 The site [13.2.4] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.4 Compliance with the law , regulations and bylaws [2.1] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.5 Provision and testing of samples of materials and goods , of finishes and assemblies of elements of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.6 Opening up of work for inspection, removal or re-execution | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.7 Removal or re-execution of work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.8 Removal or substitution of any materials and goods | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.9 Protection of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.10 Making good physical loss and repairing damage to the works [8.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.11 Rectification of defects [21.2] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.12 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion and a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.13 Expenditure of budgetary allowances , prime cost amounts and provisional sums | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.14 Appointment of a subcontractor [14.0; 15.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.15 Termination of a nominated n/s subcontract agreement [27.2.8] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.16 Work by (a) direct contractor (s) [17.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.17 Access by other or previous contractors to remedy defective work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.18 Removal from the site of any person employed on the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.19 Removal from the site of any person not engaged on or connected with the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 5.2.20 On termination, protection of the works , removal of construction equipment and surplus materials and goods [29.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?7. Wet Services engineer | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following but remove where the consultant is not relevant to this agreement. Edit both the duties and the contract instructions of the consultant in keeping with the wishes of the principal agent | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Note that the contract instructions hereinafter are those listed in clause 17.0 of the JBCC PBA | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.1 Duties : The electrical engineer is responsible for all measurements, valuations, financial assessments and all other quantity surveying and cost control functions of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2 Contract instructions [17.0] : | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.1 Rectification of discrepancies, errors in descriptions or omissions in contract documents other than this agreement | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.2 Alteration to design, standards or quantity of the works provided that such contract instructions shall not substantially change the scope of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.3 The site [13.2.4] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.4 Compliance with the law , regulations and bylaws [2.1] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.5 Provision and testing of samples of materials and goods , of finishes and assemblies of elements of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.6 Opening up of work for inspection, removal or re-execution | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.7 Removal or re-execution of work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.8 Removal or substitution of any materials and goods | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.9 Protection of the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.10 Making good physical loss and repairing damage to the works [8.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.11 Rectification of defects [21.2] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.12 A list for practical completion specifying outstanding or defective work to be rectified to achieve practical completion and a list for completion and a list for final completion specifying outstanding or defective work to be rectified to achieve final completion | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.13 Expenditure of budgetary allowances , prime cost amounts and provisional sums | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.14 Appointment of a subcontractor [14.0; 15.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.15 Termination of a nominated n/s subcontract agreement [27.2.8] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.16 Work by (a) direct contractor (s) [17.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.17 Access by other or previous contractors to remedy defective work | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.18 Removal from the site of any person employed on the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.19 Removal from the site of any person not engaged on or connected with the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 7.2.20 On termination, protection of the works, removal of construction equipment and surplus materials and goods [29.0] | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?8. Health and safety consultant | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following but remove where the consultant is not relevant to this agreement. Edit both the duties and the contract instructions of the consultant in keeping with the wishes of the principal agent | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Note that the contract instructions hereinafter are those listed in clause 17.0 of the JBCC PBA | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 8.1 Duties : The health and safety consultant is responsible for all aspects of health and safety of the works. | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Without derogating from the generality thereof, the health and safety consultant will perform the following specific functions | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 8.1.1 Act as the employer's agent in terms of Construction Regulations issued in terms of the Occupational Health and Safety Act,1993 | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 8.1.2 Prepare and update the health and safety specification for the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 8.1.3 Agree with the contractor the health and safety plan for the works | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 8.1.4 Carry out regular audits to ensure adherence to the safety plan and compliance with the Act and Regulations | [8 empty] | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 8.1.5 Stop the execution of the works where the agreed specification or plan is not adhered to | Item | 1 |  | 0 |  |  | 1 |  | 31 |  | 78710 | [12 empty] | 1 | 0 | 1 | -2 | I | I
13 | 7 | Clause 7.0 - Design responsibility | Item | 1 |  | 0 |  |  | 1 |  | 32 |  | 78720 | [12 empty] | 1 | 0 | 1 | -2 | I | I
13 |  | Insurance and security (A8 - A11) | [8 empty] | 33 |  | 78730 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
13 | 8 | Clause 8.0 - Works risk | Item | 1 |  | 0 |  |  | 1 |  | 34 |  | 78740 | [12 empty] | 1 | 0 | 1 | -2 | I | I
13 | 9 | Clause 9.0 - Indemnities | Item | 1 |  | 0 |  |  | 1 |  | 35 |  | 78750 | [12 empty] | 1 | 0 | 1 | -2 | I | I
13 | 10 | Clause 10.0 - Insurances | Item | 1 |  | 0 |  |  | 1 |  | 36 |  | 78760 | [12 empty] | 1 | 0 | 1 | -2 | I | I
13 | 11 | Clause 11.0 - Security | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | If it is deemed advisable, the EXTENT of any security for payment may be stated as follows: | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?Security for payment | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The employer shall provide to the contractor security for payment in the amount of ? ............................................... ................... Rand (R ............................) ? [11.4.1, 11.10] ? | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Where it is expected of the contractor to waive his lien in terms of clause 11.10, the waiver of lien may be extended to subcontracts as follows: | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Extension of waiver of lien | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor shall ensure that a waiver of lien is included in all subcontracts and that the works executed on the site are kept free of all liens and other encumbrances at all times [11.10] ? | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 11.5 | [8 empty] | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Replace "ten (10)" with "five (5)" | Item | 1 |  | 0 |  |  | 1 |  | 37 |  | 78770 | [12 empty] | 1 | 0 | 1 | -2 | I | I
14 |  | Execution (A12 - A17) | [8 empty] | 38 |  | 78780 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
14 | 12 | Clause 12.0 - Duties of the parties | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Provisions of clauses 12.1.2 to 12.1.6 and 12.2.18 | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Refer to the contract data, the Preliminaries document and "Section B : Preliminaries" of this Bill No. 1 with reference to the provisions of clauses 12.1.2 to 12.1.6 and 12.2.18 of the JBCC Principal Building Agreement | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Office accommodation | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor shall provide, maintain and remove on practical completion air conditioned office accommodation with suitable tables and chairs for meetings to be held on the site. Such offices shall be kept clean and fit for use at all times [12.2.18] ? | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Notice board | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor shall erect in a position approved by the principal agent, maintain and remove on practical completion a notice board recommended by the South African Institute of Architects and as approved by the principal agent listing the names and logos of the employer, the contractor, and the professional consultants. No subcontractor or supplier notice boards may be erected unless permission is granted by the principal agent for such notice boards to be erected [12.2.18] ? | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 12.1.5 requires the employer to identify access to water, sewer, stormwater and/or electricity connections to the site. | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Should such information be available then it is to be stated here or in the contract data in detail with a suitable heading in bold. | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Reference as [12.1.5]. The user should, however, note that clauses 8.1 and 8.2 of the Preliminaries state that the employer | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | does not warrant that any water or electricity supplies that may exist are adequate for the proper execution of the works. Any | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ambiguity in this respect is to be dealt with | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Should access to water, sewer, stormwater and/or electricity connections not be identifiable due to such information not being available or the specific requirements of the contractor cannot be determined, then the following clause may be considered in which event a qualified tender may be expected | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Access to water, sewer, stormwater and electricity connections | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The employer is not in a position to identify access to water, sewer, stormwater and/or electricity connections to the site as may be suitable for the execution of the works. The contractor is to allow what he considers to be required and is to qualify his tender in detail in this regard, failing which it shall be taken that the contractor has allowed what will be required for the execution of the works. In such case no claims for additional cost or loss shall be entertained [12.1.5] ? | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Statutory and other notices | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Statutory and other notices which the contractor must submit and/or comply with before possession of the site can be given are to be stated here or in the contract data. Reference [12.1.6] | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | If specific information is not available then the user may consider a clause along the following lines | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? The contractor shall submit and/or comply with all statutory and other notices that may be required by any local or other authority in order not to cause any delay to the commencement of the works by the contractor. The contractor shall pay all deposits or fees in this regard [12.1.6] | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | It is, however, specifically recorded that the employer shall be responsible for the timeous approval of building plans by any local or other authorities and the payment of any fees or charges related thereto ? | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 12.2.17 Omit the words "[CD] within ten (10) working days" | Item | 1 |  | 0 |  |  | 1 |  | 39 |  | 78790 | [12 empty] | 1 | 0 | 1 | -2 | I | I
15 | 13 | Clause 13.0 - Setting out | Item | 1 |  | 0 |  |  | 1 |  | 40 |  | 78800 | [12 empty] | 1 | 0 | 1 | -2 | I | I
15 | 14 | Clause 14.0 - Nominated subcontractors | [8 empty] | 41 |  | 78810 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 41 |  | 78810 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 14.1.4 Reference should read "[17.1.14]" | [8 empty] | 41 |  | 78810 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 14.6 Reference should read "[17.1.15; 27.1.8]" | [8 empty] | 41 |  | 78810 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 14.7.2 Reference should read "[27.1.8]" | [8 empty] | 41 |  | 78810 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 14.7.3 Reference should read "[27.2.8]" | Item | 1 |  | 0 |  |  | 1 |  | 41 |  | 78810 | [12 empty] | 1 | 0 | 1 | -2 | I | I
15 | 15 | Clause 15.0 - Selected subcontractors | [8 empty] | 42 |  | 78820 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 42 |  | 78820 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 15.2 Reference should read "[17.1.14]" | [8 empty] | 42 |  | 78820 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 15.7.2 Reference should read "[27.1.8]" | [8 empty] | 42 |  | 78820 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 15.7.3 Reference should read "[27.2.8]" | Item | 1 |  | 0 |  |  | 1 |  | 42 |  | 78820 | [12 empty] | 1 | 0 | 1 | -2 | I | I
16 | 16 | Clause 16.0 - Direct contractors | [8 empty] | 43 |  | 78830 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Attendance on direct contractors | [8 empty] | 43 |  | 78830 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | In respect of direct contractors the contractor shall: | [8 empty] | 43 |  | 78830 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 1. Designate an area for the direct contractor to establish a temporary office and workshop and storage of equipment and materials | [8 empty] | 43 |  | 78830 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 2. Allow the use of personnel welfare facilities, where provided | [8 empty] | 43 |  | 78830 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 3. Provide water, lighting and single phase electric power to a position within 50m of the place where the direct contract work is to be carried out, other than fuel or power for commissioning of any installation | [8 empty] | 43 |  | 78830 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 4. Permit the direct contractor to use erected scaffolding, hoisting facilities, etc provided by the contractor , in common with others having the like right while it remains erected on the site [16.1] | [8 empty] | 43 |  | 78830 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 43 |  | 78830 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 16.1.3 Reference should read "[26.5]" | Item | 1 |  | 0 |  |  | 1 |  | 43 |  | 78830 | [12 empty] | 1 | 0 | 1 | -2 | I | I
16 | 17 | Clause 17.0 - Contract instructions | [8 empty] | 44 |  | 78840 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Site instructions | [8 empty] | 44 |  | 78840 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Instructions issued on site are to be recorded in a site instruction book which is to be supplied and maintained on site by the contractor ? | [8 empty] | 44 |  | 78840 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 44 |  | 78840 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 17.1.3 Reference should read "[13.2.4]" | Item | 1 |  | 0 |  |  | 1 |  | 44 |  | 78840 | [12 empty] | 1 | 0 | 1 | -2 | I | I
16 |  | Completion (A18 - A24) | [8 empty] | 45 |  | 78850 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
16 | 18 | Clause 18.0 - Interim completion | Item | 1 |  | 0 |  |  | 1 |  | 46 |  | 78860 | [12 empty] | 1 | 0 | 1 | -2 | I | I
16 | 19 | Clause 19.0 - Practical completion | [8 empty] | 47 |  | 78870 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 47 |  | 78870 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | List with a suitable heading in bold any special requirements for practical completion here. Reference as [19.3.1] | Item | 1 |  | 0 |  |  | 1 |  | 47 |  | 78870 | [12 empty] | 1 | 0 | 1 | -2 | I | I
16 | 20 | Clause 20.0 - Sectional completion | [8 empty] | 48 |  | 78880 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 48 |  | 78880 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | If sectional completion is applicable, then a clause with a suitable heading in bold should be inserted, or drawing(s) annexed, to define the various sections. Reference as [20.1] | [8 empty] | 48 |  | 78880 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 48 |  | 78880 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 20.2.2 Reference should read "[21.6.2]" | Item | 1 |  | 0 |  |  | 1 |  | 48 |  | 78880 | [12 empty] | 1 | 0 | 1 | -2 | I | I
16 | 21 | Clause 21.0 - Defects liability period and final completion | [8 empty] | 49 |  | 78890 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 49 |  | 78890 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 21.1 Delete the word "final" in the second last line | [8 empty] | 49 |  | 78890 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Reference should read "[21.6.1]" | [8 empty] | 49 |  | 78890 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 21.9 Reference should read "[21.4 ; 21.6.1]" | Item | 1 |  | 0 |  |  | 1 |  | 49 |  | 78890 | [12 empty] | 1 | 0 | 1 | -2 | I | I
17 | 22 | Clause 22.0 - Latent defects liability period | Item | 1 |  | 0 |  |  | 1 |  | 50 |  | 78900 | [12 empty] | 1 | 0 | 1 | -2 | I | I
17 | 23 | Clause 23.0 - Revision of date for practical completion | [8 empty] | 51 |  | 78910 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Substitution of materials and goods | [8 empty] | 51 |  | 78910 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The removal or substitution of any materials and goods which do not conform to the specification or the contract drawings shall not constitute grounds for the extension of the construction period nor for the adjustment of the contract value [17.1.8, 23.1 & 2] | [8 empty] | 51 |  | 78910 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 51 |  | 78910 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 23.2 Reference should read "[26.7]" | [8 empty] | 51 |  | 78910 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 23.2.1 Reference should read "[12.1.7]" | Item | 1 |  | 0 |  |  | 1 |  | 51 |  | 78910 | [12 empty] | 1 | 0 | 1 | -2 | I | I
17 | 24 | Clause 24.0 - Penalty for late or non-completion | Item | 1 |  | 0 |  |  | 1 |  | 52 |  | 78920 | [12 empty] | 1 | 0 | 1 | -2 | I | I
17 |  | Payment (A25 - A27) | [8 empty] | 53 |  | 78930 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
17 | 25 | Clause 25.0 - Payment | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Materials and goods prematurely on site | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Materials and goods brought onto the site prematurely shall not be authorised for payment [25.3.2] | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert ONE of the following two clauses | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Materials and goods stored off site | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Materials and goods stored off site shall not be authorised for payment [25.3.2] ? | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Materials and goods stored off site | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Materials and goods stored off site shall be authorised for payment subject to a guarantee for advance payment being provided to the employer [25.3.2] ? | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Fluctuations in costs | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | All fluctuations in costs, with the exception of fluctuations in the rate of Value Added Tax, shall be for the account of the contractor [25.3.4] ? | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Prices submitted | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Where prices are submitted by the contractor or subcontractor during the progress of the works in respect of contract instructions or in regard to a claim under the terms of this agreement and notwithstanding the fact that such prices | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | may be used in an interim payment certificate, there is to be no presumption of acceptance. Should the principal agent wish to accept any such prices prior to the issue of the certificate of final completion, it shall be in writing | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 25.2 The word : "final" in bold in the second line | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 25.10.3 Reference should read "[25.13 ; 26.10]" | [8 empty] | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | New clause 25.12.4 Add the words : "Terminate the agreement [29.14.7] where the listed options [25.12.1-3] have failed | Item | 1 |  | 0 |  |  | 1 |  | 54 |  | 78940 | [12 empty] | 1 | 0 | 1 | -2 | I | I
18 | 26 | Clause 26.0 - Adjustment of the contract value and final account | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following where tenant installations/users requirements may be delayed or omitted | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Tenant installations/users requirements delayed | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | There is a possibility that certain works related to tenant installations/users requirements may have to be delayed and may consequently not be executed prior to practical completion | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The employer reserves the right to omit such work without compensation to the contractor for loss of profit or any other loss which the contractor may suffer as a result of such omission | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Should the contractor be instructed to do so he shall execute this work under the conditions pertaining to this agreement on the basis that a separate amount for preliminaries appurtenant to this work (if applicable) is agreed to between the contractor and the principal agent and on condition that instruction to | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | proceed with such work is given to him within a period of three (3) calendar months after the date of practical completion of the works ? | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Cost of claims | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | All costs incurred by the contractor in the preparation of claims shall be borne by the contractor. This provision shall not preclude an adjudicator or an arbitrator appointed in terms of this agreement [30.6,7] from making a determination on costs | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor shall review, assess and adjudicate any claims received by him from any subcontractor and thereafter submit same to the principal agent with a recommendation in order to assist the principal agent in adjudicating the claim [26.6] | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 26.4.2 Omit the entire clause and renumber thereafter | [8 empty] | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | New clause 26.4.3 "Other proven or unavoidable costs" | Item | 1 |  | 0 |  |  | 1 |  | 55 |  | 78950 | [12 empty] | 1 | 0 | 1 | -2 | I | I
18 | 27 | Clause 27.0 - Recovery of expense and/or loss | Item | 1 |  | 0 |  |  | 1 |  | 56 |  | 78960 | [12 empty] | 1 | 0 | 1 | -2 | I | I
18 |  | Suspension and termination (A28 - A29) | [8 empty] | 57 |  | 78970 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
18 | 28 | Clause 28.0 - Suspension by the contractor | [8 empty] | 58 |  | 78980 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 58 |  | 78980 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | New clause 28.1.5 and renumber thereafter "Or where an agent has failed to act in terms of this agreement [6.4] Clause 28.2 Replace the word "defect" with "default" in the first line | Item | 1 |  | 0 |  |  | 1 |  | 58 |  | 78980 | [12 empty] | 1 | 0 | 1 | -2 | I | I
19 | 29 | Clause 29.0 - Termination | [8 empty] | 59 |  | 78990 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Errata by JBCC | [8 empty] | 59 |  | 78990 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 29.1.2 Delete the words : "within the period stated [CD]" | [8 empty] | 59 |  | 78990 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 29.14.1 Change as follows : "Provide or maintain a guarantee for payment......[11.4 - 5]" | [8 empty] | 59 |  | 78990 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Clause 29.14.2 Reference should read "[12.1.7]" | [8 empty] | 59 |  | 78990 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | New clause 29.14.8 "Or where an agent has failed to act in terms of this agreement [6.4]" | Item | 1 |  | 0 |  |  | 1 |  | 59 |  | 78990 | [12 empty] | 1 | 0 | 1 | -2 | I | I
19 |  | Dispute resolution (A30) | [8 empty] | 60 |  | 79000 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
19 | 30 | Clause 30.0 - Dispute resolution | Item | 1 |  | 0 |  |  | 1 |  | 61 |  | 79010 | [12 empty] | 1 | 0 | 1 | -2 | I | I
19 | 31 | Agreement | [8 empty] | 62 |  | 79020 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The second sentence of the introduction where the parties sign the agreement, namely "Any provision in this agreement...… acceptance by such subcontractor at any time." is deemed to be deleted | [8 empty] | 62 |  | 79020 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The required information of the parties and the amount of the contract sum shall be inserted in the agreement for signature of the agreement by the parties | Item | 1 |  | 0 |  |  | 1 |  | 62 |  | 79020 | [12 empty] | 1 | 0 | 1 | -2 | I | I
19 | 32 | Contract data | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Payment of preliminaries | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Where Option B is applicable and the initial construction period is extended the monthly charge shall be recalculated on the same basis as was initially applied but taking into account the revised construction period and the amounts already paid to the contractor [CD26.0] | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Adjustment of preliminaries | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Where the adjustment of preliminaries is in terms of Option A, the construction period and the initial construction period shall be calculated in working days [CD 26.0] | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Where the adjustment of preliminaries is in terms of Option A and sectional completion is required, the contractor shall provide the principal agent with the division of the categorised amounts into sections. Should the contractor fail to provide such information within the period stipulated, the categorised amounts shall be prorated to the value of each section [ CD 26.0] | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Where the adjustment of preliminaries is required in terms of Option B and sectional completion is required, the contractor shall provide the principal agent with details of the resources required for each section and those that are common to sections. Should the contractor fail to provide such information within the period stipulated, Option A shall apply [CD 26.0] | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Where removal of lateral support insurance is required and stated as such in the contract data for the employer to insure, it is to be noted that it may appear under "no" for the employer to insure where the contractor is to take out the other insurances. In such a case the following clause is to be inserted | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Removal of lateral support insurance | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Whilst it is stated in clause 10.0 of the contract data that the employer will not be responsible for works and other insurances the employer shall nevertheless be responsible for the removal of lateral support insurance in the amount stated ? | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Refer to the user note on page 2 of this Bill No 1 (Preliminaries) and insert the proposed clause in the space provided in the contract data where changes made to the JBCC documentation is to be recorded should the user wish to adhere to the system of inserting amendments, modifications, corrections or supplements to the JBCC documentation under the listed clause headings in this Bill No 1 (Preliminaries) | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Tenderer's selection | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Before submission of his tender the contractor is to complete the tenderer's selection in the contract data | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | All information for the above requires consultation with the contractor. The principal agent should not pre-select any of the alternatives available to the contractor | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Note 4 on page 10 of the contract data | [8 empty] | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Note 4 on page 10 of the contract data which relates to any benefit or right in favour of any subcontractor shall be deemed to be deleted | Item | 1 |  | 0 |  |  | 1 |  | 63 |  | 79030 | [12 empty] | 1 | 0 | 1 | -2 | I | I
20 |  | SECTION B: PRELIMINARIES | [8 empty] | 64 |  | 79040 | [12 empty] | 1 | 0 | 1 | -2 | H | 0
20 |  | Interpretation (B1) | [8 empty] | 65 |  | 79050 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
20 | 33 | Clause 1.1 - Definitions | Item | 1 |  | 0 |  |  | 1 |  | 66 |  | 79060 | [12 empty] | 1 | 0 | 1 | -2 | I | I
20 | 34 | Clause 1.2 - Interpretation | Item | 1 |  | 0 |  |  | 1 |  | 67 |  | 79070 | [12 empty] | 1 | 0 | 1 | -2 | I | I
20 |  | Documents (B2) | [8 empty] | 68 |  | 79080 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
20 | 35 | Clause 2.1 - Checking of documents | Item | 1 | 2500 | 2500 |  |  | 1 |  | 69 |  | 79090 | [12 empty] | 1 | 0 | 1 | -2 | I | I
20 | 36 | Clause 2.2 - Provisional bills of quantities | [8 empty] | 70 |  | 79100 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User Note | [8 empty] | 70 |  | 79100 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Check 'wet trades' included in the bills of quantities and edit the following clause as may be necessary | [8 empty] | 70 |  | 79100 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Multiple procurement | [8 empty] | 70 |  | 79100 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | These bills of quantities are in multiple procurement format ie the 'wet trades' - earthworks, concrete, formwork and reinforcement, precast concrete, masonry, waterproofing and sub-surface drainage - are provisionally (fully?) measured and the subsequent trades are budgetary allowances and/or provisional sums ? | Item | 1 |  | 0 |  |  | 1 |  | 70 |  | 79100 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 37 | Clause 2.3 - Availability of construction information | [8 empty] | 71 |  | 79110 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Budgetary allowances and provisional sums | [8 empty] | 71 |  | 79110 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The budgetary allowances ?and/or provisional sums ? allocated for subsequent trades included in this agreement will be separately procured, based on multiple procurement of subcontractors during the construction period ? | Item | 1 |  | 0 |  |  | 1 |  | 71 |  | 79110 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 38 | Clause 2.4 - Ordering of materials and goods | Item | 1 |  | 0 |  |  | 1 |  | 72 |  | 163073 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 |  | Previous work and adjoining properties (B3) | [8 empty] | 73 |  | 79120 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
21 | 39 | Clause 3.1 - Previous work - dimensional accuracy | Item | 1 |  | 0 |  |  | 1 |  | 74 |  | 79130 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 40 | Clause 3.2 - Previous work - defects | Item | 1 |  | 0 |  |  | 1 |  | 75 |  | 79140 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 41 | Clause 3.3 - Inspection of adjoining properties | Item | 1 |  | 0 |  |  | 1 |  | 76 |  | 79150 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 |  | The Site (B4) | [8 empty] | 77 |  | 163083 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
21 | 42 | Clause 4.1 - Defined works area and project sign board | Item | 1 |  | 0 |  |  | 1 |  | 78 |  | 163093 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 43 | Clause 4.2 - Site Inspecition etc | Item | 1 | 1000 | 1000 |  |  | 1 |  | 79 |  | 163103 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 44 | Clause 4.3 - Enclosure of the works | Item | 1 |  | 0 |  |  | 1 |  | 80 |  | 163113 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 45 | Clause 4.4 - Geotechnical investigation | Item | 1 |  | 0 |  |  | 1 |  | 81 |  | 163123 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 46 | Clause 4.5 - Encroachments | Item | 1 |  | 0 |  |  | 1 |  | 82 |  | 163133 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 47 | Clause 4.6 - Existing premises occupied | Item | 1 |  | 0 |  |  | 1 |  | 83 |  | 163163 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 48 | Clause 4.7 - Services - known | Item | 1 | 10000 | 10000 |  |  | 1 |  | 84 |  | 163153 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 49 | Clause 4.8 - Protection of trees and/or relevant natural features | Item | 1 |  | 0 |  |  | 1 |  | 85 |  | 163143 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 |  | Management of Contract (B5) | [8 empty] | 86 |  | 163173 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
21 | 50 | Clause 5.1 - Management of the works | Item | 1 | 100000 | 100000 |  |  | 1 |  | 87 |  | 163183 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 51 | Clause 5.2 - Progress meetings | Item | 1 | 5000 | 5000 |  |  | 1 |  | 88 |  | 163193 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 52 | Clause 5.3 - Technical meetings | Item | 1 | 2500 | 2500 |  |  | 1 |  | 89 |  | 163203 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 |  | Samples, shop drawings and manufacturer's instructions (B6) | [8 empty] | 90 |  | 79160 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
21 | 53 | Clause 6.1 - Samples of materials | Item | 1 | 5000 | 5000 |  |  | 1 |  | 91 |  | 79170 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 54 | Clause 6.2 - Workmanship samples | Item | 1 |  | 0 |  |  | 1 |  | 92 |  | 79180 | [12 empty] | 1 | 0 | 1 | -2 | I | I
21 | 55 | Clause 6.3 - Shop drawings | Item | 1 |  | 0 |  |  | 1 |  | 93 |  | 79190 | [12 empty] | 1 | 0 | 1 | -2 | I | I
22 | 56 | Clause 6.4 - Compliance with manufacturer's instructions | Item | 1 | 1000 | 1000 |  |  | 1 |  | 94 |  | 79200 | [12 empty] | 1 | 0 | 1 | -2 | I | I
22 |  | Deposits and fees (B7) | [8 empty] | 95 |  | 79210 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
22 | 57 | Clause 7.1 - Deposits and fees | Item | 1 |  | 0 |  |  | 1 |  | 96 |  | 79220 | [12 empty] | 1 | 0 | 1 | -2 | I | I
22 |  | Temporary services (B8) | [8 empty] | 97 |  | 79230 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
22 | 58 | Clause 8.1 - Water | Item | 1 |  |  |  |  | 1 |  | 98 |  | 79240 | [12 empty] | 1 | 0 | 1 | -2 | I | I
22 | 59 | Clause 8.2 - Electricity | Item | 1 |  |  |  |  | 1 |  | 99 |  | 79250 | [12 empty] | 1 | 0 | 1 | -2 | I | I
22 | 60 | Clause 8.3 - Ablution and welfare facilities | Item | 1 |  |  |  |  | 1 |  | 100 |  | 79260 | [12 empty] | 1 | 0 | 1 | -2 | I | I
22 | 61 | Clause 8.4 - Communication facilities | Item | 1 |  |  |  |  | 1 |  | 101 |  | 79270 | [12 empty] | 1 | 0 | 1 | -2 | I | I
22 |  | Prime cost amounts (B9) | [8 empty] | 102 |  | 79280 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
22 | 62 | Clause 9.1 - Responsibility for prime cost amounts | [8 empty] | 103 |  | 79290 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 103 |  | 79290 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Where details of materials included in prime cost amounts are NOT readily available and it is therefore not possible for the contractor to price for waste, the relevant prime cost amount shall be inserted in the bills of quantities as a lump sum with the contractor being given the opportunity to separately price his overheads and profit and for taking delivery, etc as called for in this clause 9.1 of the preliminaries. In such case the fixing only or installation only of the relevant materials shall be provisionally measured for the contractor to price and shall be re-measured upon completion | [8 empty] | 103 |  | 79290 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Where details of materials for which prime cost amounts are to be allowed ARE readily available, the quantity surveyor may elect to insert the relevant prime cost amount in measured items, which measured items shall contain sufficient detail for the contractor to price for fixing and installation, waste, etc | Item | 1 |  | 0 |  |  | 1 |  | 103 |  | 79290 | [12 empty] | 1 | 0 | 1 | -2 | I | I
22 |  | Attendance on subcontractors (B10) | [8 empty] | 104 |  | 79300 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
22 | 63 | Clause 10.1 - General attendance | [8 empty] | 105 |  | 79310 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 105 |  | 79310 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | General attendance is defined as being the duties of the contractor in terms of clause 12.2 of the JBCC n/s subcontract agreement | Item | 1 |  | 0 |  |  | 1 |  | 105 |  | 79310 | [12 empty] | 1 | 0 | 1 | -2 | I | I
22 | 64 | Clause 10.2 - Special attendance | [8 empty] | 106 |  | 79320 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 106 |  | 79320 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert details after the provisional sums (nominated or selected subcontract amount) for any special attendance where specifically required for each subcontractor separately | [8 empty] | 106 |  | 79320 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | It is important to note that general attendance only requires the contractor to 'permit the subcontractor to use erected scaffolding, hoisting facilities, etc provided by the contractor, in common with others having the like right while it remains erected on the site' (refer to 12.2.13 of the JBCC n/s subcontract agreement). Many subcontractors qualify their tenders to exclude scaffolding and/or hoisting facilities. Especially scaffolding could be an expensive item and it may be necessary in order to avoid claims to require the contractor to provide for the extended use of scaffolding for specific subcontracts within a description of 'special attendance' in the applicable bill | Item | 1 |  | 0 |  |  | 1 |  | 106 |  | 79320 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 |  | General (B11) | [8 empty] | 107 |  | 79330 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
23 | 65 | Clause 11.1 - Protection of the works | Item | 1 |  |  |  |  | 1 |  | 108 |  | 79340 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 | 66 | Clause 11.2 - Protection/isolation of existing/sectionally occupied works | Item | 1 |  |  |  |  | 1 |  | 109 |  | 79350 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 | 67 | Clause 11.3 - Security of the works | Item | 1 |  |  |  |  | 1 |  | 110 |  | 79360 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 | 68 | Clause 11.4 - Notice before covering work | Item | 1 |  |  |  |  | 1 |  | 111 |  | 79370 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 | 69 | Clause 11.5 - Disturbance | Item | 1 |  |  |  |  | 1 |  | 112 |  | 79380 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 | 70 | Clause 11.6 - Environmental disturbance | Item | 1 |  |  |  |  | 1 |  | 113 |  | 79390 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 | 71 | Clause 11.7 - Works cleaning and clearing | Item | 1 |  |  |  |  | 1 |  | 114 |  | 79400 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 | 72 | Clause 11.8 - Vermin | Item | 1 |  |  |  |  | 1 |  | 115 |  | 79410 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 | 73 | Clause 11.9 - Overhand work | Item | 1 |  |  |  |  | 1 |  | 116 |  | 79420 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 | 74 | Clause 11.10 - Tenant installations by direct contractors | Item | 1 |  |  |  |  | 1 |  | 117 |  | 163213 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 | 75 | Clause 11.11 - Construction Board | Item | 1 |  |  |  |  | 1 |  | 118 |  | 163223 | [12 empty] | 1 | 0 | 1 | -2 | I | I
23 |  | Preliminaries Schedule (B12) | [8 empty] | 119 |  | 79430 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
23 | 76 | Information for completion of schedule | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Information necessary for elections and completion of those clauses contained in the preliminaries schedule which are necessary for tender purposes is given hereunder. Where no information is given it shall mean that no specific requirements are expected or that the clause is not relevant to this specific contract | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.1 - Provisional bills of quantities [2.2] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The quantities are provisional ? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.2 - Availability of construction information [2.3] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Construction documentation is complete? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.3 - Previous work - dimensional accuracy [3.1] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.4 - Previous work - defects [3.2] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.5 - Inspection of adjoining properties [3.3] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.6 - Defined works area [4.1] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User Note | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Describe the restrictions to the site or areas that the contractor may not occupy. Reference as [PBA 12.1.4] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.7 - Handover of site in stages [4.2] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Describe in detail where handover of the site to the contractor is done in stages | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.8 - Enclosure of the works [4.3] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.9 - Geotechnical investigation [4.4] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the following clause should a geotechnical investigation report be available and insert the following annexure | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ?Refer to Annexure ? For the results of a geotechnical investigation repot ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.10 Existing premises occupied [4.6] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | If the existing premises are occupied state it here and describe the detail and/or specific requirements. Reference as [PBA 12.1.2] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.11 - Services - known [4.7] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert details should the contractor be responsible for the preservation of known services. Reference as [PBA 12.1.3] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.12 - Protection of trees and/or relevant natural features [4.8] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Expand clause 4.8 of the Preliminaries should there be specific requirements for the preservation of trees or relevant natural features. Reference as [PBA 12.1.3] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.13 - Water [8.1] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Option A (by contractor) ? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Option B (by employer - free of charge) ? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Option C (by employer - metered) ? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.14 - Electricity [8.2] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Option A (by contractor) ? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Option B (by employer - free of charge) ? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Option C (by employer - metered) ? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.15 - Ablution and welfare facilities [8.3] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Option A (by contractor) ? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Option B (by employer) ? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.16 - Communication facilities [8.4] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.17 - Protection of the works [11.1] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.18 - Protection/isolation of existing/sectionally occupied works [11.2] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Protection/isolation is required ? Yes/No ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.19 - Disturbance [11.5] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The following clause may be used should "disturbance" [11.5] need to be extended | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? All work is to be carried out in such a manner as to cause no unacceptable or unreasonable dust, noise, vibrations, nuisance, inconvenience, annoyance and the like to the public, others, other properties and traffic in so far as they exceed the permissible limitations set by government legislation or by the local authority. Any delays, stoppages and the like arising from or in order to comply with the above will not constitute grounds for an adjustment to the construction period or contract value whatsoever ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | 12.20 - Environmental disturbance [11.6] | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | ? Controlling all forms of pollution | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor shall be responsible for and take all precautions in controlling by whatever means necessary all forms of pollution emanating from the site during the construction period due inter alia to noise, artificial light, wind-blown sand, dust, deposits of mud, etc | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor is to ensure that all roads which border the site and is used by the contractor during the execution of the works are kept clean and free of any dirt or debris caused by the execution of the works ? | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Environmental management plan | [8 empty] | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The employer has prepared an environmental management plan (EMP) (refer to Annexure ? for a copy of the relevant plan). The contractor shall price opposite this item for compliance with all the requirements of such EMP | Item | 1 | 25000 |  |  |  | 1 |  | 120 |  | 79440 | [12 empty] | 1 | 0 | 1 | -2 | I | I
25 |  | SECTION C: SPECIFIC PRELIMINARIES | [8 empty] | 121 |  | 79450 | [12 empty] | 1 | 0 | 1 | -2 | H | 0
25 |  | User note | [8 empty] | 122 |  | 163233 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
|  | Users shall avoid inserting in Section C items which may be construed as amending, modifying, correcting or supplementing the provisions of the JBCC Principal Building Agreement. Such amendments, modifications, corrections or supplements should be kept to the absolute minimum and should be inserted in the space provided in the contract data or in a single referenced annexure as stipulated in the contract data or, when taking into account the methodology suggested in the user note on page 2 of this Bill No. 1, should be inserted in Section A under the recited clause headings of the JBCC Principal Building Agreement in this Bill No. 1 | [8 empty] | 122 |  | 163233 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
25 |  | User note : Selected examples of typical clauses are provided to indicate ways of describing such clauses. Users must delete, adapt or add to these examples to suit their particular circumstances | [8 empty] | 123 |  | 79460 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
26 |  | Specific Preliminaries | [8 empty] | 124 |  | 163243 | [12 empty] | 1 | 0 | 1 | -2 | S | 0
26 | 77 | Warranties for materials and workmanship | [8 empty] | 125 |  | 79470 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Where warranties for materials and/or workmanship are called for, the contractor shall obtain a written warranty, addressed to the employer , from the entity supplying the materials and/or doing the work and shall deliver same to the principal agent on the final completion of the contract | [8 empty] | 125 |  | 79470 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The warranty shall state that workmanship, materials and installation are warranted for a specific period from the date of final completion and that any defects that may arise during the specified period shall be made good at the expense of the entity supplying the materials and/or doing the work, upon written notice to do so. | [8 empty] | 125 |  | 79470 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The warranty will not be enforced if the work is damaged by defects in the execution of the works , in which case the responsibility for replacement shall rest entirely with the contractor | Item | 1 |  | 0 |  |  | 1 |  | 125 |  | 79470 | [12 empty] | 1 | 0 | 1 | -2 | I | I
26 | 78 | Overtime | [8 empty] | 126 |  | 79480 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Should overtime be required to be worked for any reason whatsoever, the costs of such overtime is to be borne by the contractor unless the principal agent has specifically authorised, in writing, prior to execution thereof, that costs for such overtime are to be borne by the employer | Item | 1 |  | 0 |  |  | 1 |  | 126 |  | 79480 | [12 empty] | 1 | 0 | 1 | -2 | I | I
26 | 79 | Co-operation of the contractor for cost management | [8 empty] | 127 |  | 79490 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | It is specifically agreed that the contractor accepts the obligation of assisting the principal agent in implementing proper cost management. The contractor will be advised by the principal agent of all cost management procedures which will be implemented to ensure that the final building cost does not exceed the budget | Item | 1 |  | 0 |  |  | 1 |  | 127 |  | 79490 | [12 empty] | 1 | 0 | 1 | -2 | I | I
26 | 80 | Overloading | [8 empty] | 128 |  | 79500 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor shall take all necessary steps to ensure that no damage occurs due to overloading of any portion of the works or temporary works eg scaffolding, etc. The contractor shall submit details of his proposed loading, storage, plant erection, etc to the principal agent for approval prior to proceeding with such loading, storing or erecting and shall comply with and pay for the principal agent's requirements in connection with the provision of temporary support work, etc. Any damage caused to the works by overloading shall be made good by the contractor at his sole expense | Item | 1 |  | 0 |  |  | 1 |  | 128 |  | 79500 | [12 empty] | 1 | 0 | 1 | -2 | I | I
26 | 81 | Propping of floors below | [8 empty] | 129 |  | 79510 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor is advised that propping of floors below may be required if he wishes to use any areas of completed suspended reinforced concrete slabs for vehicle access, storage of materials and goods and location of plant, scaffolding, etc. The location of these areas and any necessary propping shall be approved by the principal agent and the cost thereof shall be borne by the contractor | Item | 1 |  | 0 |  |  | 1 |  | 129 |  | 79510 | [12 empty] | 1 | 0 | 1 | -2 | I | I
26 | 82 | Testing of flat roof waterproofing for watertightness | [8 empty] | 130 |  | 79520 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Flat roof waterproof areas shall be prepared with small sand dykes around them of a size and enclosing an area approved by the principal agent , flooded with water and kept 'ponde for at least forty (40) hours as a test to ensure the watertightness of the waterproofing and before any further construction work is carried out above the waterproofing | Item | 1 |  | 0 |  |  | 1 |  | 130 |  | 79520 | [12 empty] | 1 | 0 | 1 | -2 | I | I
27 | 83 | Green star building certification | [8 empty] | 131 |  | 79530 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | User note | [8 empty] | 131 |  | 79530 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Insert the provisions called for by the relevant green star consultant should it be a requirement that the project be submitted for green star certification | Item | 1 |  | 0 |  |  | 1 |  | 131 |  | 79530 | [12 empty] | 1 | 0 | 1 | -2 | I | I
27 | 84 | Broad based black economic empowerment (BBBEE) | [8 empty] | 132 |  | 79540 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | Tenders submitted will be evaluated taking into account their empowerment rating | [8 empty] | 132 |  | 79540 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The employer will be monitoring the black economic empowerment status of the contractor throughout the execution of the works | [8 empty] | 132 |  | 79540 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor is to submit to the principal agent on an annual basis a schedule of spend, split into vendors engaged as subcontractors and suppliers indicating their BBBEE rating including proof of the said rating | Item | 1 |  | 0 |  |  | 1 |  | 132 |  | 79540 | [12 empty] | 1 | 0 | 1 | -2 | I | I
27 | 85 | Advertising rights | [8 empty] | 133 |  | 79550 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The employer may elect to contract with advertising agencies for the erection of advertising hoardings, banners, wraps or the like for the duration of the contract. The contractor shall not prevent such an arrangement and will assist in the facilitation of same. Position and type of advertising structure to be agreed with the principal agent so as not to hinder the contractor in the meeting of his obligations under this agreement | Item | 1 |  | 0 |  |  | 1 |  | 133 |  | 79550 | [12 empty] | 1 | 0 | 1 | -2 | I | I
27 | 86 | Confidentiality | [8 empty] | 134 |  | 79560 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor undertakes to maintain in confidence any and all information regarding this project and shall obtain appropriate similar undertakings from all subcontractors and suppliers. Such information shall not be used in any way except in connection with the execution of the works | [8 empty] | 134 |  | 79560 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | No information regarding this project shall be published or disclosed without the prior written consent of the employer | Item | 1 |  | 0 |  |  | 1 |  | 134 |  | 79560 | [12 empty] | 1 | 0 | 1 | -2 | I | I
27 | 87 | Media releases | [8 empty] | 135 |  | 79570 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | All rights of publication of articles in the media, together with any advertising relating thereto or in any way connected with this project, shall vest with the employer | [8 empty] | 135 |  | 79570 | [12 empty] | 1 | 0 | 1 | -2 | I | I
|  | The contractor together with his subcontractors shall not, without the prior written consent of the employer, cause any statement or advertisement to be printed, screened or aired by the media | Item | 1 |  | 0 |  |  | 1 |  | 135 |  | 79570 | [12 empty] | 1 | 0 | 1 | -2 | I | I
27 |  | SUMMARY OF CATEGORIES | [8 empty] | 136 |  | 79580 | [12 empty] | 1 | 0 | 1 | -2 | H | 0
27 |  | Category : Fixed R........................... Category : Value R........................... Category : Time R........................….. | [8 empty] | 137 |  | 79590 | [12 empty] | 1 | 0 | 1 | -2 | C | 0
Bill Total

## External Works-Fencing
ITEM | DESCRIPTION | UOM | QUANTITY | RATE | AMOUNT
SECTION NO.2
BILL No. 2 : EXTERNAL WORKS - FENCE
Site Clearance
1 | Taking down the exting fence including removal of timber poles and store in a secure place and handing it over to the client after the completion of the project. | m | 75 | 0 | 0
2 | Making good to existing vehicle gate opening and install new sliding gate to fit in the existing opening | No | 1 | 0 | 0
3 | Repairing to the damged poles and fence as indicated on the drawings | item | 1 | 0 | 0
EXCAVATIONS
4 | Grade 25 Mpa concrete footing measuring 400x400x60mm on each post | m3 | 1.152 | 0 | 0
Cochrane Cleavu Fence or Equally Approved;
5 | "Chochrane ClearVu Invisible Wall Panels" or equally approved consisting of 3,305m panel width x 2,4m Height with3,5mm diameter coated wire | m | 315 | 0 | 0
6 | a) Galvanized, then Marine Fusion Bond coated (acid modified) Tampered post | No. | 95 | 0 | 0
7 | b) Galvanized, then Marine Fusion Bond coated (acid modified) square post | No. | 8 | 0 | 0
8 | c) Supply and install 100mm x 1,65m length galvanized, then marine fusion bond coated (acid modified) shark tooth spikes | m | 315 | 0 | 0
9 | d) Supply and Install anti-burrow measuring 300mm CV underdig x 3,05m bitumen dipped | m | 315 | 0 | 0
GATES, ETC
Cleavu or eqaully approved Single leaf pedestrian gate including lock, etc complete
10 | a) 1,2m x 2,4m galvanized, then Marine Fusion Bond coated (acid modified) swing pedestane gate mechanically made | No. | 1 | 0 | 0
GATES, ETC
Single leaf pedestrian gate including lock, etc complete
11 | a) 1,2m x 2,4m galvanized, then Marine Fusion Bond coated (acid modified) swing pedestane gate | No. | 1 | 0 | 0
Single leaf vehicular gate including lock, etc complete
12 | a) 5m x 2,4m galvanized, then Marine Fusion Bond coated (acid modified) sliding gate | No. | 1 | 0 | 0
GATE MOTORS
a) Sliding gate motor system comprising back-up battery, anti-theft cage, anti-shock wheels, track, vehicle loop detector (Allow a Prime Cost Amount of R7500/system delivered to site) fixed in position, complete:
13 | b) For steel gate approximately 5m wide | No | 2 | 0 | 0
| carried to collection |  |  |  | 0
SECTION NO.4
BILL NO.13 - EXTERNAL WORKS (PROVISIONAL)
COLLECTION
| Total BROUGHT FORWARD from 3 |  |  |  | 0
| carried to summary |  |  |  | 0

## Electrical works
ITEM | DESCRIPTION | UOM | QUANTITY | RATE | AMOUNT
SECTION NO.2
BILL No.3 : ELECTRICAL WORKS
1 | 16mm2 2 core | m | 55 | 0 | 0
2 | 10mm2 2 core | m | 500 | 0 | 0
Cable Termination
3 | 16mm2 2 core | m | 2 | 0 | 0
4 | 10mm2 2 core | m | 15 | 0 | 0
Trenching
5 | 600x400mm | m3 | 133.2 | 0 | 0
6 | 600X600 Main Hole | No. | 2 | 0 | 0
Bare Earth Conductor
7 | 10mm2 | m | 55 | 0 | 0
8 | 6mm2 | m | 500 | 0 | 0
New Meter
10 | Connection fees | No. | 1 | 0 | 0
11 | Standing Kioks | No. | 1 | 0 | 0
12 | Smart meter | No. | 1 | 0 | 0
Light Fittings
0
13 | 400W Solar LED Street Lights installed at 5-7m pole height including 8m pole planted at 1-1,2m | No. | 8 | 0 | 0
| carried to summary |  |  |  | 0

## Prov Sum
ITEM | DESCRIPTION | UOM | QUANTITY | RATE | AMOUNT
SECTION 2
BILL No.4: PROVISIONAL SUMS
Insert preambles/specifications as may be required or in order to supplement any applicable preambles, specifications or bills of quantities descriptions. Take note that these Model Bills of Quantities utilise abbreviated descriptions. The Model Preamble
BUDGETARY ALLOWANCES
1 | Allow for the Sum of R 6500.00 for the payment of CLO per month | Item | 1 | 26000 | 26000
2 | Allow for the sum of R 300 per member x 4 for PSC meetings | Item | 1 | 4800 | 4800
3 | Provide the sum of R 100000.00 for tree felling by a nominated subcontractor. | Prov Sum | 1 | 100000 | 100000
4 | Handling fee and profit | % | 100000 | 10% | 10000
5 | Provide the sum of R 15 000.00 for land survey | Prov sum | 1 | 15000 | 15000
6 | Handling fee and profit | % | 15000 | 10% | 1500
7 | Provide the sum of R 5 000.00 for traffic service rerouting | Prov Sum | 1 | 5000 | 5000
8 | Handling fee for item 5,1,8 | % | 5000 | 10% | 500
| carried to collection |  |  |  | 162800
SECTION NO.4
BILL NO.16 - PROVISIONAL SUMS
COLLECTION
| Total BROUGHT FORWARD from 3 |  |  |  | 162800
| carried to summary |  |  |  | 162800

## Final Summary
FINAL SUMMARY -
| DESCRIPTION | AMOUNT
1 | PRELIMINARIES | 0
2 | BILL No. 2 : EXTERNAL WORKS - FENCE | 0
3 | BILL No.3 : ELECTRICAL WORKS | 0
4 | BILL No.4: PROVISIONAL SUMS | 162800
| SUB TOTAL | 0
| Add 10% Project Contigency | 0
| TOTAL BEFORE VAT | 0
ADD:
| VALUE ADDED TAX (V.A.T at 15%) | 0
| TOTAL TENDER SUM | 0